## MicrosoftAdoptionChecklist
Microsoft 365
Short Form Adoption Planning Checklist
Utilize this checklist to begin your planning process. Import into Microsoft Lists or add additional content as needed in your organization. Ask questions in our Community at https://aka.ms/DriveAdoption.
Task ID | Task | Description | Status | Assigned To | Due Date | Start Date | End Date
1 | Identify technology enablement team members | Identify adoption specialist / user experience staff, IT technical staff, executives, and other stakeholders for the core team | Not Started
2 | Plan an execute a technology & business overview session | Recruit technology providers and business leaders to share knowledge about key product features and potential business scenarios for improvement. Use for fact finding, prioritization and stakeholder alignment. | Not Started
3 | Design user experience strategy including end user support and readiness communications plan | Use Microsoft Adoption Community and produt resources for guidance. Customize for your industry or business group. | Not Started
4 | Complete technical readiness work including configuration of engagement community | Prepare tenant for healthy deployment per Microsoft recommendations. Shared activity with user experience staff to ensure accuracy of launch materials. | Not Started
5 | Select early adopter / rapid deployment program users | Select employees who will use new capabilities and share feedback. Group by similiar role, department or business process | Not Started
6 | Train internal Champions | Onboard and train peer to peer Champion team to provide support and guidance during end user onboarding and initial usage of product | Not Started
7 | Schedule learning series activities | Utilize Viva Learning materials to supplement those created internally. Get inspiration from adoption.microsoft.com user onboarding kits. | Not Started
8 | Deploy licenses | In the Microsoft Admin Center | Not Started
9 | Schedule executive onboarding (including executive staff) | White glove onboarding sessions for executives | Not Started
10 | Kick off user communications series with welcome email from Exec Stakeholder and invite into Community of Practice | Implement ongoing communications to new users to drive learning series attendance, community engagement and product usage | Not Started
11 | Schedule feedback roundtables and community calls | Provide employee only opportunities to provide feedback on features | Not Started
12 | Review Adoption Score reporting with enablement team & exec staekholders | Establish collaboration best practice baselines; drive meaningful awareness of success. | Not Started
13 | Create feedback analysis workstream | Participate in internal and Microsoft-led feedback sessions | Not Started
14 | Implement executive white glove sessions | Invite executive level staff to thought | Not Started
15 | Conduct service health review | Review service usage & health against selected AI-ready scenarios and support ticket volumes and open issues. Validate AI-ready roadmap. | Not Started
16 | Nominate success stories | Identify successful scenarios that have been impacted by product usage to share | Not Started
17 | Plan for phase two of adoption work | Deliver continuous learning to workforce; select key scenarios for further technical modernization; ensure extensibility governance and training program in place that also inlcudes low-code and non traditional development staff (e.g. Makers) | Not Started

## Values (hidden)
Status
Not Started
In Progress
Pending Info
Blocked
Completed
Deferred